## Instructions
Instructions | Enter your team name as specified in the cell below. When doing cross-team acceptance testing, enter the name for the testing group. Fill-in the Test Plan worksheet with all the remaining User Stories in your Product Backlog. Since Product acceptance is from the perspective of the end-user, only add User Stories that pertain to the Owner or Buyer and do not include User Stories specifically for the REST API service (e.g. AS a developer...). As your user stories are refined, add the acceptance criteria for each user story. Use a separate worksheet to provide any specific test case data that the tester needs to use. As tests are performed in each sprint, indicate Pass/Fail. Note that there are separate columns for each sprint. The tester should add initials and a date in the comments column. If the test failed, the tester is required to add additional information about the failure. The status cell will color code based on the test results. The comments cell will color code when a test result exists but no information is entered. Save this test plan with a name formatted as "term-swen-261-sec-letter name", e.g. 2171-swen-261-10-a Speedy Racers.xslx. Submit this file per the instructions specified for the sprint submissions and cross-team testing.
2221-swen-261-5-E-Engenuity | Your team name as "term-swen-261-sec-letter name", e.g. 2171-swen-261-10-a Speedy Racers
Testing Team Name | fill in when doing cross-team testing

## Test Plan
User Story | Acceptance Criterion | Sprint 2 | Tester initials; date; comments (required if test failed) | Sprint 3 | Tester initials; date; comments (required if test failed)
As a buyer I want to see a list of products so that I choose what to purchase. | Given that I am on the e-store site when I am not on the Products page then I must see a means to navigate to the Products page.
Given that I am not on the Products page when I choose the Products page then I am taken to the Products page.
Given that I am on the Products page when there are no products in the inventory I see a message indicating that that there are no products available.
| Given that I am on the products page when there are products in the inventory then I see each product and short description. |  |  |  |  | delete everything
Given that I am on the products page when there are products in the inventory then I see a means to add each product to my shopping cart.
As an Admin I want to add new products to the inventory so that I can expand my business. | Given I am not an admin, when I view the website, then I will not see an option to add products. | Pass | JD; 10/16/22; Looks good, I do not see an option to add products on the user side.
| Given I am an admin, when I select the option to add a product to the inventory, with inputs for name, quantity, and price, then the product will be added. | Pass | JD; 10/16/22; Looks good, I see an option on admin side.
As a Buyer, I want to be able to look at a list of Products so I can find products I want to buy | Given There Are Products in the system when I visit the website then I see a list of all of the products | Pass | GB; 10/18/22; Looks great! Meets acceptance criteria! Digital candy for making it its own component and creating cards component.
As a User I want to login with a username so that I can access the E-store. | Given I am not logged in when I open the website then I can log into my account. | Pass | JD; 10/18/22; Everything works well. One small note is that it's a little disconnected, on the splashscreen you click log in instead of it just appearing. Other than that it works fine.
As a Buyer I want to checkout with the products I selected so that I can purchase and have them. | Given a user's shopping cart has items available for purchase when the user attempts to checkout then the user takes those items from the inventory and the cart is cleared. | Pass | ZW; 10/19/22; Looks good. Meets acceptance criteria. The tests also all pass... Under further investigation, the products class does not have a hash code, so the remove from cart does not work. This has been added and now function correctly.
| Given a user's shopping cart has one or more items unavailable for checkout when the user attempts to checkout then the user is unable to checkout | Pass | ZW; 10/19/22; Looks good. Meets acceptance criteria and passes tests! I like how you implemented the refresh cart function!
As a Buyer, I want to be able to search for Products so I can find products I want to buy | Given I am a user when I input a string into a designated textbox then I expect a list of products. | Pass | GB; 10/19/22; Visually awkard, but functional.
As an Admin I want to remove products from the inventory so that the E-Store displays we don't carry the product anymore. | Given I am an admin when I select an option to remove a product from the inventory, then the product is removed from the inventory. | Pass | GB; 10/19/22; Looks great Tim, keep up the good work 👍
As a User I want to login with a username so that I can access the E-store. | Given I am not logged in when I open the website then I can log into my account. | Pass | TA; 10/19/22; This looks great! However, I don't think we need a user component, it is functionally identical to the home page, and the minor differences can be implemented there.
|  | Pass | TA; 10/19/22; Your fixes look great, nice job!
As an Admin I want to add new products to the inventory so that I can expand my business. | Given I am logged in as an admin when I select an item in the inventory then I can change its price and quantity in the backend. | Pass | JD; 10/19/22; Looks great, css bug looks annoying but it functions