## Instructions
Instructions | Enter your team name as specified in the cell below. When doing cross-team acceptance testing, enter the name for the testing group. Fill-in the Test Plan worksheet with all the remaining User Stories in your Product Backlog. Since Product acceptance is from the perspective of the end-user, only add User Stories that pertain to the Owner or Buyer and do not include User Stories specifically for the REST API service (e.g. AS a developer...). As your user stories are refined, add the acceptance criteria for each user story. Use a separate worksheet to provide any specific test case data that the tester needs to use. As tests are performed in each sprint, indicate Pass/Fail. Note that there are separate columns for each sprint. The tester should add initials and a date in the comments column. If the test failed, the tester is required to add additional information about the failure. The status cell will color code based on the test results. The comments cell will color code when a test result exists but no information is entered. Save this test plan with a name formatted as "term-swen-261-sec-letter name", e.g. 2171-swen-261-10-a Speedy Racers.xslx. Submit this file per the instructions specified for the sprint submissions and cross-team testing.
2221-swen-261-5-E-Engenuity | Your team name as "term-swen-261-sec-letter name", e.g. 2171-swen-261-10-a Speedy Racers
Testing Team Name | fill in when doing cross-team testing

## Test Plan
User Story | Acceptance Criterion | Sprint 2 | Tester initials; date; comments (required if test failed) | Sprint 3 | Tester initials; date; comments (required if test failed)
As a buyer I want to see a list of products so that I choose what to purchase. | Given that I am on the e-store site when I am not on the Products page then I must see a means to navigate to the Products page.
Given that I am not on the Products page when I choose the Products page then I am taken to the Products page.
Given that I am on the Products page when there are no products in the inventory I see a message indicating that that there are no products available.
| Given that I am on the products page when there are products in the inventory then I see each product and short description. |  |  |  |  | delete everything
Given that I am on the products page when there are products in the inventory then I see a means to add each product to my shopping cart.
As an Admin I want to add new products to the inventory so that I can expand my business. | Given I am not an admin, when I view the website, then I will not see an option to add products. | Pass | JD; 10/16/22; Looks good, I do not see an option to add products on the user side.
| Given I am an admin, when I select the option to add a product to the inventory, with inputs for name, quantity, and price, then the product will be added. | Pass | JD; 10/16/22; Looks good, I see an option on admin side.
As a Buyer, I want to be able to look at a list of Products so I can find products I want to buy | Given There Are Products in the system when I visit the website then I see a list of all of the products | Pass | GB; 10/18/22; Looks great! Meets acceptance criteria! Digital candy for making it its own component and creating cards component.
As a User I want to login with a username so that I can access the E-store. | Given I am not logged in when I open the website then I can log into my account. | Pass | JD; 10/18/22; Everything works well. One small note is that it's a little disconnected, on the splashscreen you click log in instead of it just appearing. Other than that it works fine.
As a Buyer I want to checkout with the products I selected so that I can purchase and have them. | Given a user's shopping cart has items available for purchase when the user attempts to checkout then the user takes those items from the inventory and the cart is cleared. | Pass | ZW; 10/19/22; Looks good. Meets acceptance criteria. The tests also all pass... Under further investigation, the products class does not have a hash code, so the remove from cart does not work. This has been added and now function correctly.
| Given a user's shopping cart has one or more items unavailable for checkout when the user attempts to checkout then the user is unable to checkout | Pass | ZW; 10/19/22; Looks good. Meets acceptance criteria and passes tests! I like how you implemented the refresh cart function!
As a Buyer, I want to be able to search for Products so I can find products I want to buy | Given I am a user when I input a string into a designated textbox then I expect a list of products. | Pass | GB; 10/19/22; Visually awkard, but functional.
As an Admin I want to remove products from the inventory so that the E-Store displays we don't carry the product anymore. | Given I am an admin when I select an option to remove a product from the inventory, then the product is removed from the inventory. | Pass | GB; 10/19/22; Looks great Tim, keep up the good work 👍
As a User I want to login with a username so that I can access the E-store. | Given I am not logged in when I open the website then I can log into my account. | Pass | TA; 10/19/22; This looks great! However, I don't think we need a user component, it is functionally identical to the home page, and the minor differences can be implemented there.
|  | Pass | TA; 10/19/22; Your fixes look great, nice job!
As an Admin I want to add new products to the inventory so that I can expand my business. | Given I am logged in as an admin when I select an item in the inventory then I can change its price and quantity in the backend. | Pass | JD; 10/19/22; Looks great, css bug looks annoying but it functions
As a customer I want to add multiple copies of Pokémon cards to my shopping cart so that I can buy multiple of them. | Given I have no copies of a specific Pokémon card in my cart when I add that card to my cart then I want to have one of those cards in my cart. |  |  | Pass | ZW; 10/23/22; Looks Good and Unit Test Passes!
| Given I have one or more copies of a specific Pokémon card in my cart when I add that card to my cart then I want to have the quantity of that card in my cart to increase. |  |  | Pass | ZW; 10/23/22; I like the addition of incrementing the number of cards in the users cart.
| Given I have the same quantity of a single card in my cart compared to the inventory when I add that card to my cart again then I shouldn't be able to add the card to my cart. |  |  | Pass | ZW; 10/23/22; I agree nobody should be able to add more to their cart than what is in the Inventory.
| Given I go to purchase the Pokémon cards in my cart when the inventory has adequate stock of all the cards in my cart then I want to be able to checkout all of the cards in my cart. |  |  | Pass | ZW; 10/23/22 Looks Great!
| Given I go to purchase the Pokémon cards in my cart when the inventory has less stock of one or more of the cards in my cart then I want to be stopped when trying to checkout the cards in my cart. |  |  | Pass | ZW; 10/23/22 Good Job
| Given I have more than one copy of a specific Pokémon card in my cart when I delete one of that card from my cart then I want to have the quantity of that card in my cart to decrease. |  |  | Pass | ZW; 10/23/22; Unit Tests pass!
| Given I have one copy of a specific Pokémon card in my cart when I delete that card from my cart then I want that card in my cart to be removed from my cart. |  |  | Pass | ZW; 10/23/22; Looks good, Tests Pass!
As an admin, I want order history to be saved, so I can make informed decisions regarding the E-Store inventory. | Given I am a customer, when I place an order, then my order information should be saved, along with a timestamp and an order number |  |  | Pass | DP; 11/2/22; I have used curls and determined that this works!
| Given I am a customer, when I place more than one order, both orders should be saved, along with a timestamp and different order numbers |  |  | Pass | DP; 11/2/22; I have used curls and determined that this works!
| Given I am a user, when I request to see my order history, all of my past orders should be returned |  |  | Pass | DP; 11/2/22; I have looked at the unit tests and determined that this works in theory!
As a user I want to register my account with a password so that my account for the e-store is protected. | Given that I am on the login page when I look to the register user form then I expect to see a field for password and password re-entry. |  |  | Pass | ZW; 11/4/22; Looks Good! I see a place where a user can set up their account with a password. Setting up the account works!
As a user I want to be able to change my password so that I am not stuck with my original password. | Given I am logged in as a user when I navigate to account then I expect to be able to change my password. |  |  | Pass | ZW; 11/4/22; Looks Good! I see a place where a user can chnage their password on their user page. Changing password works!
As a User I want to add products to my shopping cart visually so that I can see the products in my cart and purchase them. | Given The card is in stock and I have none of that card in my cart when I select to add the card to my cart then I expect to see the card in my cart with a quantity of 1. |  |  | Pass | TA; 11/5/2022; I added a Pikachu to my empty cart, and I now see it in my cart with a quantity of 1
| Given The card is not in stock and I have none of that card in my cart when I look to select add to cart then I expect to not be able to add to cart. |  |  | Pass | TA; 11/5/2022; Trying to add one out of stock item displays "One or more items in your cart have changed". Also, adding another card to your cart before attempting to add 3 of the same out of stock card makes it appear in the cart, but leaving and re-entering the shopping cart clears the out of stock card from the cart.
|  |  |  | Pass | TA; 11/5/2022; Attemting the same procedures now doesn't let me add it to the cart, or display a message
| Given The card is in stock and I have one or more of that card in my cart when I select to add the card to my cart then I expect to see the card in my cart with an incremented quantity. |  |  | Pass | TA; 11/5/2022; I added a second Pikachu to my cart, and it appears in my cart with a quantity of 2
| Given I have more than one of a specific card in my cart when I select to add one of the specific card from my cart then I expect to see the card in my cart capped at the quantity in the inventory. |  |  | Pass | TA; 11/5/2022; I added 40 squirtles to the cart, and tried to add another from both the home page and the shopping cart, and the quantity remained at 40.
| Given I have one of a specific card in my cart when I select to remove the card from my cart then I expect to see the card disappear from my cart. |  |  | Pass | TA; 11/5/2022; I decremented a card with a quantity of 1, and it disappeared from the cart.
| Given I have more than one of a specific card in my cart when I select to remove one of the specific card from my cart then I expect to see the card in my cart decremented by 1. |  |  | Pass | TA; 11/5/2022; I decremented a card with a quantity of 3, and it got a quantity of 2 instead.
| Given something changes in the inventory that has implications on my cart when I look at my cart then I expect to be informed. |  |  | Pass | TA; 11/5/2022; I had 2 cards in the cart, and changed the quantity of one card to 0, and deleted the other. Upon looking at the cart again, both cards were removed from my cart, and the message "One or more items in your cart have changed or are no longer available" was displayed.
As an Admin I want to have types, so I can better represent products in the backend | Given I am a customer when I see a product on the front end, then I see the type of that product |  |  | Pass | ZW;11/8/22; Looks good and it works!
| Given I am an admin, when I create a product, I am able to select type(s) for the card. |  |  | Pass | ZW;11/8/22; Looks good and it works!
As a Buyer I want to checkout with the products I selected so that I can purchase and have them. | 1. GIVEN the user has added items to their shopping cart WHEN the user selects to checkout THEN the user should be prompted for credit card |  |  | Pass | JD; 11/7/2022; Looks Good.
| 2. GIVEN the user has entered their credit card information WHEN the user selects to continue checkout THEN the user should be prompted for shipping information |  |  | Pass | JD; 11/7/2022; Looks All good
| 3. GIVEN the user has entered their shipping information WHEN the user selects to finish checkout THEN the user should be notified that their order has went through |  |  | Pass | JD; 11/7/2022; It works! I am a fool
| 4. GIVEN the user has started the checkout process WHEN the user selects to cancel checkout THEN the user should be sent back to the initial shopping cart |  |  | Pass | JD; 11/7/2022; Marginal Pass, it's fine
As an admin I want to create more admins so that as the store expands we have the moderation for the store we need. | Given I am logged in as admin and am on the admin dashboard when I Enter the information for creating an admin then I expect a new admin account to be made in the system. |  |  | Pass | 11/8/22 DP I created a new admin after entering all the correct information in. It works!
| Given I am logged in as admin and am on the admin dashboard when I Enter incorrect information for creating an admin then I expect a new admin account to not be made in the system. |  |  | Pass | 11/8/22 DP It correctly didn't create a new admin after I didn't enter correct information. It works!
As a user I want to be able to change my password so that I am not stuck with my original password. | Given I am logged in as a user when I navigate to account then I expect to be able to change my password. |  |  | Pass | 11/8/22 DP I went to my user page and I can see the ability to change password!
| Given I am logged in as a user when I enter a new password and don't enter my current password then I expect to be stopped when trying to change the password |  |  | Pass | 11/8/22 DP It correctly stopped me when I tested this. It works!
| Given I am logged in as a user when I enter a new password and enter my current password then I expect to change my password in the system |  |  | Pass | 11/8/22 DP It worked correctly when changing my password when giving my old password correctly. It works!
As an admin I want to change my password so that I can regularly change my password to keep the e-store secure. | Given I am logged in as an admin when I navigate to my account view then I am offered a form where I can change my password. |  |  | Pass | 11/8/22 DP I went to the admin dashboard as an admin and found a way to change my password!
| Given I am logged in as an admin when I enter a new password and don't enter my current password then I expect to be stopped when trying to change the password |  |  | Pass | 11/8/22 DP It correctly stopped me when trying to change my password when giving the wrong current password. It works!
| Given I am logged in as an admin when I enter a new password and enter my current password then I expect to change my password in the system |  |  | Pass | 11/8/22 DP It changed the password in the system correctly!
As a Admin I want to have pages that I can only access so that the Store can be secure. | Given I am logged out when I type in the URL /admin then I expect to not be routed to the /admin page |  |  | Pass | 11/8/22 DP It stopped me correctly. It works!
| Given I am logged in as a normal user when I type in the URL /admin then I expect to not be routed to the /admin page |  |  | Pass | 11/8/22 DP It stopped me correctly. It works!
| Given I am logged in as admin when I type in the URL /admin then I expect to have access to the admins dashboard |  |  | Pass | 11/8/22 DP I was correctly let into the admin page. It works!
| Given I am logged in when I refresh the page then I should stay logged in and nothing should change |  |  | Pass | 11/8/22 DP Can Confirm this did what it was supposed to do. It works!
As a User I want to have a shopping cart that I can only access when I am logged in so that the information can be secure. | Given I am logged in when I refresh the page then I should stay logged in and nothing should change |  |  | Pass | 11/8/22 DP Can Confirm this did what it was supposed to do. It works!
| Given I am Logged in as a normal user when I type a different UserName in the url path then I expect nothing to change on the page |  |  | Pass | 11/8/22 DP This works!
| Given I am logged in as admin when I type in the URL /user;username=(users name) then I expect to not be routed to the page |  |  | Pass | 11/8/22 DP This works!
| Given I am logged in as a user when I type in the URL /user;username=(users name) then I expect to be routed to the page |  |  | Pass | 11/8/22 DP This works!
| Given I am logged out when I type in the URL /user; username=(users name) then I expect to not be routed to the page |  |  | Pass | 11/8/22 DP This works!
As a user I want to register my account with a password so that my account for the e-store is protected. | Given that I am on the login page when I look to the register user form then I expect to see a field for password and password re-entry. |  |  | Pass | 11/8/22 DP I logged in as a user and found a place to add a password!
| Given that I enter a valid username and password into the username box and first password box when I enter the same password into the password validation box then I expect to have my account created. |  |  | Pass | 11/8/22 DP I created an account after putting in the valid information. It works!
| Given that I enter a valid username and an invalid password into the username box and first password box when I enter the same password into the password validation box then I expect to not have my account created |  |  | Pass | 11/8/22 DP I was stopped when I didn't use a valid password! It works!
| Given that I enter a valid username and a valid password into the username box and first password box when I enter a different password into the password validation box then I expect to not have my account created |  |  | Pass | 11/8/22 DP I was stopped when I didn't enter the same password in the validation box! It works!
| Given that I enter an invalid username or password into the username box and first password box when I enter the same or different password into the password validation box then I expect to not have my account created. |  |  | Pass | 11/8/22 DP I was stopped when I tried a combination of invalid and valid usernames and passwords! It works!
As a User, I want to search the server by type so I can find what I want to buy quickly | Given I have entered text into the search bar, When I click on one type button, then I expect pokemon of that type with that text in its name to be in the search results |  |  | Pass | ZW;11/8/22; Looks good and it works!
| Given I have entered text into the search bar, When I click on two or more type buttons, then I expect pokemon with all of those types and that text in its name to be in the search results |  |  | Pass | ZW;11/8/22; Looks good and it works!
| Given I have entered text into the search bar, When I click on no type buttons, then pokemon with the text in its name are shown, regardless of type |  |  | Pass | ZW;11/8/22; Looks good and it works!
| Given I have not entered text into the search bar, When I click on one type button, then pokemon of that type will appear, regardless of their name |  |  | Pass | ZW;11/8/22; Looks good and it works!
| Given I have not entered text into the search bar, When I click on two or more type buttons, then pokemon with those types will appear, regardless of their name |  |  | Pass | ZW;11/8/22; Looks good and it works!
| Given I have not entered text into the search bar, When I click on no type buttons, then all pokemon will appear |  |  | Pass | ZW;11/8/22; Looks good and it works!
As a User I want to see my past order history so that I have receipts of all the purchases I have made to keep track of purchases and protect against fraudulent or accidental purchases. | Given I am a user and I have purchased one or more orders of goods when I go to my order history in my user profile then I expect to see a list of all my orders and what I purchased. |  |  | Pass | DP;11/13/22; Looks good and it works!
| Given I am a user and I have not purchased any orders when I go to my order history in my user profile then I expect to not see any past orders. |  |  | Pass | DP;11/13/22; Looks good and it works!